## Sheet1
Item | TimeNeeded | Deadline | Feb Wk3 | Feb Wk4 | Mar Wk1 | Mar Wk2 | Mar Wk3 | Mar Wk4 | Apr Wk1 | Apr Wk2 | Apr Wk3 | Apr Wk4 | May Wk1 | May Wk2 | May Wk3 | May Wk4 | Jun Wk1 | Jun Wk2 | Jun Wk 3 | Jun Wk4 | July Wk1 | July Wk2 | July Wk3 | July Wk4
Meet with Jon P | 1 day | 2021-02-23 | bar: Feb Wk4
Identify cluster constraints for running Freebayes Meeting with Shobana and Mariana | 1 day | 2021-02-25 | bar: Feb Wk4
Run Freebayes | 3 weeks | 2021-04-01 | bar: Mar Wk2 to Mar Wk4
Set up website | 3 days | 2021-04-01 | bar: Mar Wk2 to Mar Wk4
Read about BCFtools
Writing - Methods 1-3 para | 2 days | 2021-03-20 | bar: Mar Wk3
Decide SNP Filtering Criteria | 1-2 days
Writing - Results Phenotypes | 5 days | 2021-03-29 | bar: Mar Wk2 to Mar Wk4
read about LD decay | 1 day | 2021-03-20 | bar: Mar Wk3
LD decay analysis
SNP thinning for LD - "core set of SNPs"
Population Structure
Neutral parameterization
Statistical Analysis
Haplotype Structure
Draft of Intro
Draft of Methods
Micromilling
Project Deadline | submit chapter | 2021-07-01